## Sheet1
Task ID | Task Desription | Start Date | NO. days to complete | Stop Date | Assigned to | Gantt chart:
EXP-1 | Order all parts and materials | 2015-12-09 | 5 | 2015-12-13 | Julin & Owen
EXP-2 | Design electronic schematic | 2015-12-11 | 13 | 2015-12-23 | Melvyn & Jonathan
EXP-3 | Assamble hardware chassis | 2016-01-02 | 4 | 2016-01-05 | Melvyn & Jonathan
EXP-4 | Design software structure | 2015-12-13 | 4 | 2015-12-16 | Jonathan & Julian
EXP-5 | Code, assamble and test DHT22 sensor | 2015-12-14 | 6 | 2015-12-19 | Owen
EXP-6 | Code, assamble and test L298N driver | 2015-12-14 | 5 | 2015-12-18 | Julian
EXP-7 | Code, assamble and test LDR | 2015-12-14 | 3 | 2015-12-16 | Owen
EXP-8 | Code, assamble and test 10DOF sensor | 2016-01-06 | 5 | 2016-01-10 | Melvyn & Jonathan
EXP-9 | Build remote control | 2015-12-17 | 10 | 2015-12-26 | Jonathan
EXP-10 | Design software UI interface | 2015-12-17 | 30 | 2016-01-15 | Owen & Julian
EXP-11 | Code, assamble and test NRF2401 module | 2015-12-18 | 16 | 2016-01-02 | Melvyn
EXP-12 | Write firmware integration with hardware | 2016-01-04 | 16 | 2016-01-19 | Melvyn & Jonathan
EXP-13 | Interface UI software with hardware | 2016-01-05 | 18 | 2016-01-22 | Owen & Julian
EXP-14 | Initial hardware integration tests | 2016-01-23 | 2 | 2016-01-24 | Jonathan & Owen
EXP-15 | Update software & hardware according to test results | 2016-01-24 | 15 | 2016-02-07 | Melvyn,Jonathan,Owen & Julian
EXP-16 | Write first draft of Project Report | 2016-01-20 | 10 | 2016-01-29 | Melvyn,Jonathan,Owen & Julian
EXP-17 | Re-test hardware and software functionality | 2016-01-29 | 3 | 2016-01-31 | Melvyn & Julian
EXP-18 | Update software & hardware according to test results | 2016-01-31 | 12 | 2016-02-11 | Melvyn,Jonathan,Owen & Julian
EXP-19 | Calibrate hardware | 2016-02-11 | 3 | 2016-02-13 | Jonathan & Julian
EXP-20 | Write report | 2016-02-15 | 18 | 2016-03-03 | Melvyn & Owen
EXP-21 | Write presentation | 2016-02-24 | 6 | 2016-02-29 | Jonathan & Julian
EXP-22 | Review write up | 2016-03-03 | 2 | 2016-03-04 | Jonathan & Julian
EXP-23 | Final software and tweaks | 2016-02-21 | 6 | 2016-02-26 | Melvyn,Jonathan,Owen & Julian
EXP-24 | Submit robot and presentation | 2016-03-06 | 2 | 2016-03-07 | Melvyn,Jonathan,Owen & Julian
Formulas:
Stop Date = [Start Date]+[NO. days to complete]-1